## Foglio1
Task ID | Nome | Andrea De Pasquale | Carmine Boninfante | Francesco Festa | Lorenzo Milione | Nicolò Gallotta | Sara Valente | Dario Mazza | Nicolò Delogu
BH-4 | Introduction |  |  | R |  |  | A | C | C
BH-6 | Scenarios | R | R | A, R | R | R | R | C | C
BH-7 | Use Cases | R | R | A, R | R | R | R | C | C
BH-8 | Current System | A |  |  |  | R |  | C | C
BH-9 | Proposed System's Overview | I | I | I | R | A, I | I | C | C
BH-10 | Identify Functional Requirements | R | R | R | R | A, R | R | C | C
BH-11 | Write Functional Requirements | I | R | I | R |  | A, I | C | C
BH-12 | Identify Non-Functional Requirements | R | A, R | R | R | R | R | C | C
BH-13 | Write Non-Functional Requirements | I | R | I | R |  | A, I | C | C
BH-14 | Identify Actors | R |  |  | A |  | I | C | C
BH-15 | User Stories | R | R |  | A |  |  | C | C
BH-16 | Use Case Diagram | A |  |  |  |  | R | C | C
BH-18 | Class Diagram | I | A, I | R | I | I | R | C | C
BH-19 | Object Table | I | I | R | I | A, I | R | D | C
BH-21 | Statechart Diagrams |  |  | A | R | R |  | C | C
BH-23 | Sequence Diagram UC_CA | A |  |  | R | R |  | C | C
BH-24 | Sequence Diagram UC_NA | R | R |  | A |  |  | C | C
BH-25 | Sequence Diagram UC_PI |  | A | R |  |  | R | C | C
BH-27 | Mock-ups |  |  |  | R | R | A | C | C
BH-28 | Navigational Path | I | I |  | R | R | A | C | C
BH-29 | RAD Integration | R | R | A, R | R | R | R | C | C
BH-30 | Prepare Glossary | R | R |  | A |  |  | C | C
BH-32 | Prepare Introduction | A | I |  |  | R |  | C | C
BH-33 | Current Software Architecture | I | R | I |  | A, I |  | C | C
BH-35 | Prepare Panoramica | A |  |  |  | R |  | C | C
BH-36 | Subsystems Decomposition | R | I | R |  | A |  | C | C
BH-37 | Hardware/Software Mapping and Deployement Diagram | I | R | I | A |  |  | C | C
BH-39 | ER Schema |  |  | A |  |  | R | C | C
BH-40 | Logical Schema |  |  | A |  |  | R | C | C
BH-41 | Data Dictionary |  |  | A |  |  | R | C | C
BH-42 | Access Control and Global Control Flow |  | A |  | LM |  |  | C | C
BH-43 | Boundary Conditions |  | A |  | LM |  |  | C | C
BH-45 | GestioneUtente | R |  | R | I | A |  | C | C
BH-46 | GestioneArnia | R |  | R | I | A |  | C | C
BH-47 | Gestione Sensori | R |  | R | I | A |  | C | C
BH-48 | PrevisioneAnomalie | R |  | R | I | A |  | C | C
BH-49 | Glossary | A, I | I | I | R | I | I | C | C
BH-50 | SDD Revision | R | R | A, R | R | R | R | C | C
BH-58 | Test Plan | R | R | R | A, R | R | R | C, R | C, R
BH-59 | Test Case Specification | R | A, R | R | R | R | R | C | C
BH-52 | Introduction |  | I | I | R | A |  | C | C
BH-53 | Packages | A, I | R | R |  | I | I | C | C
BH-54 | Class Interfaces | R |  | R | A | R | R | C | C
BH-55 | Class Diagram | I | I | R | I | A, I | R | C | C
BH-56 | Design Patterns | R | R | A, R | R, I | R | R | C | C
BH-57 | Glossary |  | A |  | R |  |  | C | C
BH-66 | Back-end Development | R |  | R | A | R | R | C | C
BH-67 | Front-End Development |  | R |  | R |  | A | C | C
BH-61 | Test Incident Report | R | A, R | R | R | R | R | C | C
BH-62 | Test Summary Report | A, R | R | R | R | R | R | C | C
BH-63 | Test Incident Report Table | R | R | R | R | A, R | R | C | C
BH-69 | Unit Testing | I | R | A, I | R | I | R | C | C
BH-70 | System Testing | R |  | R | A | R |  | C | C
BH-72 | User Manual |  | R | A |  |  | R | C | C
BH-73 | Installation Manual | R |  |  | R |  | A | C | C